## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | Failed login with correct username and correct password | Low | 1 | 20 | Use the planned debugging time in the iteration.
2 | 1 | Bid for a section | "Available courses" column still shows courses that user has already bidded | High | 5 |  | Use the planned debugging time in the iteration.
3 | 1 | Bootstrap | Not displaying size of section accurately due to calling wrong variable | High | 5 |  | Use the planned debugging time in the iteration.
4 | 1 | Bootstrap | Calling session_start() twice in processfile.php | Low | 1 |  | Use the planned debugging time in the iteration.
5 | 1 | Bootstrap | Undefined offset warning due to explode function | Low | 1 |  | Use the planned debugging time in the iteration.
6 | 1 | Bootstrap | Various echo calls seen | Low | 1 |  | Use the planned debugging time in the iteration.
7 | 1 | Login (Admin) | Header redirect warnings | High | 5 |  | Use the planned debugging time in the iteration.
8 | 1 | Bootstrap | Cannot bid for sections with bidding amount which have decimal places | Low | 1 |  | Use the planned debugging time in the iteration.
9 | 2 | Bootstrap | Upon deployment, bootstrap.php unable to successfully delete user-made temp folder | Critical | 10 | 34 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
10 | 2 | Login (User) | When login attempt, fatal error message "table boss.adminstrator doesn’t exist" | High | 5 |  | Use the planned debugging time in the iteration.
11 | 2 | Starting and clearing rounds | No bidding money refunded to unsuccessful users | Low | 1 |  | Use the planned debugging time in the iteration.
12 | 2 | Bootstrap | Common.php calls for nonexistent table during app initialisation | Low | 1 |  | Use the planned debugging time in the iteration.
13 | 2 | Login (User) | For new user, unknown database 'boss' | Critical | 10 |  | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
14 | 2 | Bid for a section | Processbid Expected 5 Parameters, provided with 4 | Low | 1 |  | Use the planned debugging time in the iteration.
15 | 2 | Bid for a section | Accessing bidding page when round is closed by going to URL directly | Low | 1 |  | Use the planned debugging time in the iteration.
16 | 2 | Bid for a section | Wrong error message when no sections are selected | Low | 1 |  | Use the planned debugging time in the iteration.
17 | 2 | Bid for a section | Enrolled 3 courses but still allowed to bid >=3 courses in next round | Low | 1 |  | Use the planned debugging time in the iteration.
18 | 2 | Bid for a section | When bidding for courses, it allows it to go through even though theres clashes with enrolled courses | Low | 1 |  | Use the planned debugging time in the iteration.
19 | 2 | Bootstrap | Able to start/close rounds even without bootstrapping | Low | 1 |  | Use the planned debugging time in the iteration.
20 | 2 | Bid for a section | Placing bids with clashed exam time return wrong error message "Clashed class time" | Low | 1 |  | Use the planned debugging time in the iteration.
21 | 3 | Bid for a section | Bids recorded are not in 2 dp, hence when updating it refunds the wrong amount | Low | 1 | 24 | Use the planned debugging time in the iteration.
22 | 3 | Drop a section | Wrong error message when section is dropped | Low | 1 |  | Use the planned debugging time in the iteration.
23 | 3 | View bidding results | Cannot view bids that have failed | Low | 1 |  | Use the planned debugging time in the iteration.
24 | 3 | Login (User) | Validation error for password | High | 5 |  | Use the planned debugging time in the iteration.
25 | 3 | Starting and clearing rounds | Minimum bid not updated upon filling last vacancy in section | High | 5 |  | Use the planned debugging time in the iteration.
26 | 3 | Drop a section | Unable to drop section successfully | High | 5 |  | Use the planned debugging time in the iteration.
27 | 3 | Starting and clearing rounds | Last bid clash not compared in closing round | Low | 1 |  | Use the planned debugging time in the iteration.
28 | 3 | Starting and clearing rounds | Unable to update bid successfully | High | 5 |  | Use the planned debugging time in the iteration.
29 | 4 | Starting and clearing rounds | No blank token validation for bid-dump, dump, user-dump. | Low | 1 | 55 | Use the planned debugging time in the iteration.
30 | 4 | Starting and clearing rounds | Unable to retabulate min bid after update bid in JSON | High | 5 |  | Use the planned debugging time in the iteration.
31 | 4 | Starting and clearing rounds | Min bid not updated in processround2bid.php | High | 5 |  | Use the planned debugging time in the iteration.
32 | 4 | Starting and clearing rounds | Json encode removes decimal point. | Low | 1 |  | Use the planned debugging time in the iteration.
33 | 4 | Starting and clearing rounds | Common bids status does not display latest status | High | 5 |  | Use the planned debugging time in the iteration.
34 | 4 | Update-bid JSON | Enrolled courses still show clashing timetables in update-bid JSON | Low | 1 |  | Use the planned debugging time in the iteration.
35 | 4 | Update-bid JSON | File specific validation errors not sorted in alphabetical order | Low | 1 |  | Use the planned debugging time in the iteration.
36 | 4 | e$ not updated when round 1 closed in UAT testing | e$ not updated when round 1 closed in UAT testing | High | 5 |  | Use the planned debugging time in the iteration.
37 | 4 | User interface | CSS was accidently commented out | Low | 1 |  | Use the planned debugging time in the iteration.
38 | 4 | Bidding | Need to show other section information for existing bids | Low | 1 |  | Use the planned debugging time in the iteration.
39 | 4 | JSON bootstrap | Student bidding for mods outside of own school in round 1 | High | 5 |  | Use the planned debugging time in the iteration.
40 | 4 | JSON bootstrap | Whitespaces inside section field | Low | 1 |  | Use the planned debugging time in the iteration.
41 | 4 | JSON bootstrap | Non-leap year had more than 28 days in certain months | Low | 1 |  | Use the planned debugging time in the iteration.
42 | 4 | JSON bootstrap | Output value as float and preserve zero point | Low | 1 |  | Use the planned debugging time in the iteration.
43 | 4 | JSON bootstrap | Blank section was not detected | Low | 1 |  | Use the planned debugging time in the iteration.
44 | 4 | JSON bootstrap | Wrong number of proper lines being printed | Low | 1 |  | Use the planned debugging time in the iteration.
45 | 4 | JSON bootstrap | Bootstrap not showing incomplete prereqs when bidding | High | 5 |  | Use the planned debugging time in the iteration.
46 | 4 | JSON bootstrap | bid.csv erros not displaying in correct order | Low | 1 |  | Use the planned debugging time in the iteration.
47 | 4 | JSON bootstrap | Zero size same as blank | Low | 1 |  | Use the planned debugging time in the iteration.
48 | 4 | JSON bootstrap | Invalid start appearing twice | Low | 1 |  | Use the planned debugging time in the iteration.
49 | 4 | JSON bootstrap | Invalid section being allowed into database | High | 5 |  | Use the planned debugging time in the iteration.
50 | 4 | JSON bootstrap | Output errors not in alphabetical order | Low | 1 |  | Use the planned debugging time in the iteration.
51 | 4 | JSON bootstrap | Class timetable clash- same course, different section | High | 5 |  | Use the planned debugging time in the iteration.
52 | 5 | User interface | Timetable exclude displaying Saturday/Sunday | Low | 1 | 8 | Use the planned debugging time in the iteration.
53 | 5 | JSON BidStatus | Min(array) but array has 0 elements. | Low | 1 |  | Use the planned debugging time in the iteration.
54 | 5 | JSON BidStatus | When no bids, error returns undefined variable | Low | 1 |  | Use the planned debugging time in the iteration.
55 | 5 | JSON BidStatus | Text in bidstatus shows "edollar" instead of "balance" | Low | 1 |  | Use the planned debugging time in the iteration.
56 | 5 | JSON BidStatus | After closing round 1, successfularray returns empty array, hence unable to continue | Low | 1 |  | Use the planned debugging time in the iteration.
57 | 5 | Bootstrap | When running manual UAT, completed_courses showed the wrong number of errors on AWS even though correct number of errors was shown on localhost | Low | 1 |  | Use the planned debugging time in the iteration.
58 | 5 | View bidding results | File not found when student account visits bidding results page | Low | 1 |  | Use the planned debugging time in the iteration.
59 | 5 | JSON BidStatus | amount and edollar not displayed in 1 decimal place | Low | 1 |  | Use the planned debugging time in the iteration.
60 | 5 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | Failed login with correct username and correct password | Resolved | 2019-09-27 | 2019-09-27 | GC & JW
2 | 1 | Bid for a section | "Available courses" column still shows courses that user has already bidded | Resolved | 2019-09-27 | 2019-10-05 | GC & ST
3 | 1 | Bootstrap | Not displaying size of section accurately due to calling wrong variable | Resolved | 2019-09-27 | 2019-09-27 | LS & YZ
4 | 1 | Bootstrap | Calling session_start() twice in processfile.php | Resolved | 2019-09-27 | 2019-09-27 | JW & ST
5 | 1 | Bootstrap | Undefined offset warning due to explode function | Resolved | 2019-09-27 | 2019-09-27 | LS & YZ
6 | 1 | Bootstrap | Various echo calls seen | Resolved | 2019-09-27 | 2019-09-27 | LS & YZ
7 | 1 | Login (Admin) | Header redirect warnings | Resolved | 2019-09-27 | 2019-09-27 | LS & YZ
8 | 1 | Bootstrap | Cannot bid for sections with bidding amount which have decimal places | Resolved | 2019-09-27 | 2019-09-27 | LS & YZ
9 | 2 | Bootstrap | Upon deployment, bootstrap.php unable to successfully delete user-made temp folder | Resolved | 2019-10-01 | 2019-10-01 | LS & GC
10 | 2 | Login (User) | When login attempt, fatal error message "table boss.adminstrator doesn’t exist" | Resolved | 2019-10-03 | 2019-10-03 | LS & GC
11 | 2 | Starting and clearing rounds | No bidding money refunded to unsuccessful users | Resolved | 2019-10-05 | 2019-10-05 | ST & YZ
12 | 2 | Bootstrap | Common.php calls for nonexistent table during app initialisation | Resolved | 2019-10-05 | 2019-10-06 | LS & GC
13 | 2 | Login (User) | For new user, unknown database 'boss' | Resolved | 2019-10-05 | 2019-10-06 | GC & ST
14 | 2 | Bid for a section | Processbid Expected 5 Parameters, provided with 4 | Resolved | 2019-10-11 | 2019-10-11 | GC & ST
15 | 2 | Bid for a section | Accessing bidding page when round is closed by going to URL directly | Resolved | 2019-10-12 | 2019-10-12 | GC & ST
16 | 2 | Bid for a section | Wrong error message when no sections are selected | Resolved | 2019-10-12 | 2019-10-12 | GC & ST
17 | 2 | Bid for a section | Enrolled 3 courses but still allowed to bid >=3 courses in next round | Resolved | 2019-10-12 | 2019-10-12 | GC & ST
18 | 2 | Bid for a section | When bidding for courses, it allows it to go through even though theres clashes with enrolled courses | Resolved | 2019-10-12 | 2019-10-12 | GC & ST
19 | 2 | Bootstrap | Able to start/close rounds even without bootstrapping | Resolved | 2019-10-12 | 2019-10-12 | GC & ST
20 | 2 | Bid for a section | Placing bids with clashed exam time return wrong error message "Clashed class time" | Resolved | 2019-10-12 | 2019-10-12 | GC & ST
21 | 3 | Bid for a section | Bids recorded are not in 2 dp, hence when updating it refunds the wrong amount | Resolved | 2019-10-19 | 2019-10-19 | JW & YZ
22 | 3 | Drop a section | Wrong error message when section is dropped | Resolved | 2019-10-19 | 2019-10-19 | JW & YZ
23 | 3 | View bidding results | Cannot view bids that have failed | Resolved | 2019-10-19 | 2019-10-19 | JW & YZ
24 | 3 | Login (User) | Validation error for password | Resolved | 2019-10-21 | 2019-10-23 | JW & YZ
25 | 3 | Starting and clearing rounds | Minimum bid not updated upon filling last vacancy in section | Resolved | 2019-10-21 | 2019-10-23 | JW & YZ
26 | 3 | Drop a section | Unable to drop section successfully | Resolved | 2019-10-21 | 2019-10-23 | JW & YZ
27 | 3 | Starting and clearing rounds | Last bid clash not compared in closing round | Resolved | 2019-10-21 | 2019-10-23 | JW & YZ
28 | 3 | Starting and clearing rounds | Unable to update bid successfully | Resolved | 2019-10-21 | 2019-10-23 | JW & YZ
29 | 4 | Starting and clearing rounds | No blank token validation for bid-dump, dump, user-dump. | Resolved | 2019-10-25 | 2019-10-27 | JW & YZ
30 | 4 | Starting and clearing rounds | Unable to retabulate min bid after update bid in JSON | Resolved | 2019-10-25 | 2019-10-27 | JW & YZ
31 | 4 | Starting and clearing rounds | Min bid not updated in processround2bid.php | Resolved | 2019-10-25 | 2019-10-27 | JW & YZ
32 | 4 | Starting and clearing rounds | Json encode removes decimal point. | Resolved | 2019-10-25 | 2019-10-27 | JW & YZ
33 | 4 | Starting and clearing rounds | Common bids status does not display latest status | Resolved | 2019-10-25 | 2019-10-27 | JW & YZ
34 | 4 | Update-bid JSON | Enrolled courses still show clashing timetables in update-bid JSON | Resolved | 2019-10-29 | 2019-10-29 | GC & ST
35 | 4 | Update-bid JSON | File specific validation errors not sorted in alphabetical order | Resolved | 2019-11-01 | 2019-11-01 | GC & ST
36 | 4 | Round 1 and 2 clearing logic | e$ not updated when round 1 closed in UAT testing | Resolved | 2019-11-02 | 2019-11-05 | GC & ST
37 | 4 | User interface | CSS was accidently commented out | Resolved | 2019-11-02 | 2019-11-05 | GC & ST
38 | 4 | Bidding | Need to show other section information for existing bids | Resolved | 2019-11-02 | 2019-11-05 | GC & ST
39 | 4 | JSON bootstrap | Student bidding for mods outside of own school in round 1 | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
40 | 4 | JSON bootstrap | Whitespaces inside section field | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
41 | 4 | JSON bootstrap | Non-leap year had more than 28 days in certain months | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
42 | 4 | JSON bootstrap | Output value as float and preserve zero point | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
43 | 4 | JSON bootstrap | Blank section was not detected | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
44 | 4 | JSON bootstrap | Wrong number of proper lines being printed | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
45 | 4 | JSON bootstrap | Bootstrap not showing incomplete prereqs when bidding | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
46 | 4 | JSON bootstrap | bid.csv erros not displaying in correct order | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
47 | 4 | JSON bootstrap | Zero size same as blank | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
48 | 4 | JSON bootstrap | Invalid start appearing twice | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
49 | 4 | JSON bootstrap | Invalid section being allowed into database | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
50 | 4 | JSON bootstrap | Output errors not in alphabetical order | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
51 | 4 | JSON bootstrap | Class timetable clash- same course, different section | Resolved | 2019-11-11 | 2019-11-11 | SL & JW
52 | 5 | User interface | Timetable exclude displaying Saturday/Sunday | Resolved | 15/11/2019 | 15/11/2019 | GC & ST
53 | 5 | JSON BidStatus | Min(array) but array has 0 elements. | Resolved | 15/11/2019 | 15/11/2019 | GC & ST
54 | 5 | JSON BidStatus | When no bids, error returns undefined variable | Resolved | 15/11/2019 | 15/11/2019 | GC & ST
55 | 5 | JSON BidStatus | Text in bidstatus shows "edollar" instead of "balance" | Resolved | 15/11/2019 | 15/11/2019 | GC & ST
56 | 5 | JSON BidStatus | After closing round 1, successfularray returns empty array, hence unable to continue | Resolved | 15/11/2019 | 15/11/2019 | GC & ST
57 | 5 | Bootstrap | When running manual UAT, completed_courses showed the wrong number of errors on AWS even though correct number of errors was shown on localhost | Resolved | 2019-11-16 | 2019-11-16 | ST & JW
58 | 5 | View bidding results | File not found when student account visits bidding results page | Resolved | 2019-11-16 | 2019-11-16 | ST & JW
59 | 5 | JSON BidStatus | amount and edollar not displayed in 1 decimal place | Resolved | 2019-11-15 | 2019-11-15 | ST & GC
60 | 5