## Week 4
Person | Question | Week 4: 9 Sep 2019 to 15 Sep 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | Work on other modules' projects and homework | Create project GIT and file structure. Attend weekly project meeting Learn about bootstrap Did the basic UI for the student bidding dashboard with Joshua | Go through class slides on bootstrap and study the lab and code examples | Did the bidding feature (remove, add bid, display bids, bidDAO) with Joshua and Giles | Full day of other projects and schoolwork Did not manage to do the student login Did some minor debugging of addBid feature and uploaded/edited SQL files for all to load temporary tables and data | At freelance job until evening | At freelance job until late at night
| What will you do today? | Create project GIT and file structure. Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples | Do the bidding feature (remove, add bid, display bids, bidDAO) | Full day of other projects and schoolwork Try to work on the student login if possible | At freelance job until evening - won't be able to work on project | At freelance job until evening - won't be able to work on project | Other project meeting. Plan for Monday weekly meeting.
| Do you have any obstacles? | No | No | No | No | No | No | No
Joshua | What did you do yesterday? | Work on other modules' projects and homework | Attend weekly project meeting Learn about bootstrap Programmed the basic UI for the student bidding dashboard with Sue | Finalise and upload meeting minutes Go through class slides on bootstrap and study the lab and code examples | Worked on BidDAO, display user's bid and drop bid feature with Sue-Anne. User class and UserDAO | Work on other modules' projects and homework. Continue the addBid feature. | Continue the addBid feature. | Continue the addBid feature.
| What will you work on today? | Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples | Work on bidding feature with Sue-Anne | Work on other modules' projects and homework Continue the addBid feature | Continue the addBid feature. | Continue the addBid feature. | Continue the addBid feature.
| Do you have any obstacles? | No | No | No | Yes, needed Sue-Anne to upload/edit the SQL files to create the tables for testing on the system | No | No | No
Giles | What did you do yesterday? | Work on other modules' projects and homework | Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples | Worked on BidDAO, display user's biddable courses and partial addBid feature with Sue-Anne | expand on studentDashboard UI | expand on studentDashboard UI | expand on studentDashboard UI
| What will you work on today? | Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples | Work on bidding feature with Sue-Anne | expand on studentDashboard UI | expand on studentDashboard UI | expand on studentDashboard UI | expand on studentDashboard UI
| Do you have any obstacles? | No | No | No | No | No | No | No
Sherman | What did you do yesterday? | Work on other modules' projects and homework | Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples Did the Connection manager, admin and user functions | Refined the schedule tracking sheetc Continued researching bootstrap | Work on other modules' projects and homework Will see what else I can work on if there's time | Continue trying bootstrap | Continue trying bootstrap
| What will you work on today? | Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples Do the Connection manager, admin and user functions | Continue researching bootstrap | Work on other modules' projects and homework Will see what else I can work on if there's time | Continue trying bootstrap | Continue trying bootstrap | Continue trying bootstrap
| Do you have any obstacles? | No | No | No | No | No | No | No
YZ | What did you do yesterday? | Work on other modules' projects and homework | Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples Do the Connection manager, admin and user functions with Sherman | Continue researching bootstrap | Work on other modules' projects and homework Will see what else I can work on if there's time | Work on other modules' projects and homework Will see what else I can work on if there's time | Work on other modules' projects and homework Will see what else I can work on if there's time
| What will you work on today? | Attend weekly project meeting Learn about bootstrap | Go through class slides on bootstrap and study the lab and code examples | Continue researching bootstrap | Work on other modules' projects and homework Will see what else I can work on if there's time | Work on other modules' projects and homework Will see what else I can work on if there's time | Work on other modules' projects and homework Will see what else I can work on if there's time | Work on other modules' projects and homework Will see what else I can work on if there's time
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 5
Person | Question | Week 5: 16 Sep 2019 to 22 Sep 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | Other project meeting. Plan for Monday weekly meeting. | Monday project meeting Addbid with Joshua | Rest | Impromptu coding session in between project meeting with Giles | Pair programming with Josh on addBid Made some constants for the round implementation | At work | At work
| What will you do today? | Monday project meeting Addbid with Joshua | Rest | Full day of other project meetings until 10pm | Pair programming with Josh on addBid | At work | Take a short nap and then go back to work | Take a short nap and then go back to work
| Do you have any obstacles? | No | No | No | No | No | No | No
Joshua | What did you do yesterday? | Continue the addBid feature. | Monday project meeting Continue the addBid feature | Continue the addBid feature. | Continue the addBid feature. | Continue the addBid feature with Sue | Continue the addBid feature. | Continue the addBid feature.
| What will you work on today? | Monday project meeting Continue the addBid feature | Continue the addBid feature. | Continue the addBid feature. | Continue the addBid feature with Sue | Continue the addBid feature. | Continue the addBid feature with Giles | Continue the addBid feature.
| Do you have any obstacles? | No | No | No | No | No | No | No
Giles | What did you do yesterday? | expand on studentDashboard UI | Monday project meeting Implement View timetable in dashboard | Help with moving the records from the old to new project schedule template | Login feature Tidy up and upload the minutes | Other project work | Other project work | Other project work
| What will you work on today? | Monday project meeting Addbid with Joshua | Help with moving the records from the old to new project schedule template Login feature Tidy up and upload the minutes | Login feature Tidy up and upload the minutes | Other project work | Other project work | Pair program the addBid feature with Josh | Other project work
| Do you have any obstacles? | No | No | No | No | No | No | No
Sherman | What did you do yesterday? | Continue trying bootstrap | Monday project meeting Work on bootstrap with Yizhou | Continue with the bootstrap | Continue with the bootstrap | Continue with the bootstrap | Continue with the bootstrap | Continue with the bootstrap
| What will you work on today? | Monday project meeting Work on bootstrap with Yizhou | Continue with the bootstrap | Continue with the bootstrap | Continue with the bootstrap | Continue with the bootstrap | Continue with the bootstrap | Continue with the bootstrap
| Do you have any obstacles? | No | No | No | No | No | No | No
YZ | What did you do yesterday? | Work on other modules' projects and homework Will see what else I can work on if there's time | Monday project meeting Work on bootstrap with Sherman | Come up with the testing cases | Come up with the testing cases | Continue with the testing cases | Continue with the testing cases Assist Sherman with Bootstrap | Continue with the testing cases Assist Sherman with Bootstrap
| What will you work on today? | Monday project meeting Work on bootstrap with Sherman | Come up with the testing cases | Continue with the testing cases | Continue with the testing cases | Continue with the testing cases Assist Sherman with Bootstrap | Continue with the testing cases Assist Sherman with Bootstrap | Continue with the testing cases Assist Sherman with Bootstrap
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 6
Person | Question | Week 6: 23 Sep 2019 to 29 Sep 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | At work until late | Project meeting Merge completed features | Work on the PM paperwork | Busy day: Full day of other project meetings | Busy day: Full day of other project meetings | SPM meeting Integrate bootstrap with remaining parts of project | Slides
| What will you do today? | Project meeting | Work on the PM paperwork | help josh with addbid help sherman with bootstrap | Busy day: Full day of other project meetings | SPM meeting Integrate bootstrap with remaining parts of project | Slides | Slides
| Do you have any obstacles? | No | No | No | No | No | No | No
Joshua | What did you do yesterday? | Continue the addBid feature. | Project meeting | Complete the addbid Help with the PM paperwork | addbid feature | addbid feature | SPM meeting Integrate bootstrap with remaining parts of project | Slides
| What will you work on today? | Continue the addBid feature. | Complete the addbid Help with the PM paperwork | addbid feature | addbid feature | SPM meeting Integrate bootstrap with remaining parts of project | Slides | Slides
| Do you have any obstacles? | No | No | No | No | No | No | No
Giles | What did you do yesterday? | addbid feature | Project meeting Merge completed features addbid feature | bids dao functions Complete addbid feature | Help with the PM paperwork addbid feature | Help with the PM paperwork | SPM meeting Integrate bootstrap with remaining parts of project | Slides
| What will you work on today? | addbid feature | bids dao functions Help with the PM paperwork addbid feature | Help with the PM paperwork addbid feature | Help with the PM paperwork addbid feature | SPM meeting Integrate bootstrap with remaining parts of project | Slides | Slides
| Do you have any obstacles? | No | No | No | No | No | No | No
Sherman | What did you do yesterday? | Continue with the bootstrap | Completed the bootstrap | Fix some stuff on the bootstrap | Fix some stuff on the bootstrap | Prepare meeting minutes | SPM meeting Integrate bootstrap with remaining parts of project Fix some stuff on the bootstrap | Slides
| What will you work on today? | Continue with the bootstrap | Help with the PM paperwork | Fix some stuff on the bootstrap | Prepare meeting minutes | SPM meeting Integrate bootstrap with remaining parts of project Fix some stuff on the bootstrap | Slides | Slides
| Do you have any obstacles? | No | No | No | No | No | No | No
YZ | What did you do yesterday? | Continue with the testing cases | Assist Sherman with Bootstrap | Help with the PM paperwork | Help with the PM paperwork | Help with the PM paperwork | Help with the PM paperwork | Slides
| What will you work on today? | Continue with the testing cases Assist Sherman with Bootstrap | Help with the PM paperwork | Help with the PM paperwork | Help with the PM paperwork | Help with the PM paperwork | Slides | Slides
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 7
Person | Question | Week 7: 30 Sep 2019 to 6 Oct 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | Check through bug metrics for PM Review | PM Review Receive allocation of work for Iteration 2 | Begin on admin rounds setting | Continue with admin rounds setting | Complete half of round 1 setting | Complete round 1 | Integrate functionalities
| What will you do today? | Practice QnA for PM Review | Begin on admin rounds setting | Rest (sick) | Continue with admin rounds setting | Continue with remaining half of round 1 setting | Group meeting | Work
| Do you have any obstacles? | No | No | Admin rounds logic is more complex then expected | No | No | No | No
Joshua | What did you do yesterday? | Check through critical path for PM Review | Make necessary changes in schedule according to feedback from PM Review | Met instructor with Sherman | Revise schedule due to setting admin rounds needing more time to complete | Not a working day | Check bug log and bug metrics | Integrate functionalities
| What will you work on today? | Practice QnA for PM Review. Assign tasks to the team as the new PM | Work on Pm Paper work Book rooms for upcoming meetings | Revise schedule due to setting admin rounds needing more time to complete | Not a working day | Plan meeting days for recess week | Group meeting | Rest
| Do you have any obstacles? | No | No | No | No | No | No | No
Giles | What did you do yesterday? | Check through slides for PM Review | PM Review Receive allocation of work for Iteration 2 | Work on secure log ins | Include password verify on login.php | Display current bids and enrolled courses in timetable | Finish displaying current bids and enrolled courses in timetable | Integrate functionalities
| What will you work on today? | Practice QnA for PM Review | Work on secure log ins | Work on displaying current bid & enrolled courses in timetable | Display current bids and enrolled courses in timetable | Continue with displaying current bids and enrolled courses in timetable | Group meeting | Rest
| Do you have any obstacles? | No | No | No | No | No | No | No
Sherman | What did you do yesterday? | Check through bug metrics for PM Review | PM Review Receive allocation of work for Iteration 2 | Work on password hashing | Include password verify on login.php | Display current bids and enrolled courses in timetable | Finish displaying current bids and enrolled courses in timetable | Integrate functionalities
| What will you work on today? | Practice QnA for PM Review | Work on password hashing | Work on displaying current bid & enrolled courses in timetable | Display current bids and enrolled courses in timetable | Continue with displaying current bids and enrolled courses in timetable | Group meeting | Rest
| Do you have any obstacles? | No | No | No | No | No | No | No
YZ | What did you do yesterday? | Check through critical path for PM Review | PM Review Receive allocation of work for Iteration 2 | Begin on admin rounds setting | Continue admin rounds setting | Complete half of round 1 setting | Complete round 1 | Integrate functionalities
| What will you work on today? | Practice QnA for PM Review | Begin on admin rounds setting | Continue admin rounds setting | Continue admin rounds setting | Continue with remaining half of round 1 setting | Group meeting | Rest
| Do you have any obstacles? | No | No | Admin rounds logic is more complex then expected | No | No | No | No

## Week 8
Person | Question | Week 8: 7 Oct 2019 to 13 Oct 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | Try to fix login admin functionality | Process successful bids for round 2 | Continue successful bids | Work on other projects | Continue successful bids | Group meeting Test cases | Group meeting Handle bugs
| What will you do today? | Process successful bids for round 2 | Continue successful bids | Work on other projects | Continue successful bids | Group meeting Test cases | Group meeting Manual Test cases | Slides for presentation Rehearse for presentation
| Do you have any obstacles? | No | No | No | No | No | No | No
Joshua | What did you do yesterday? | Work on other projects | Revise scheduling | Check up on JSON files | Work on other projects | JSON files | Group meeting Test cases | Group meeting JSON files
| What will you work on today? | Read up on JSON requirements | Rest | Work on other projects | JSON files | Group meeting Test cases | Group meeting JSON files | Slides for presentation Rehearse for presentation
| Do you have any obstacles? | No | No | No | No | No | No | No
Giles | What did you do yesterday? | Work on other projects | Drop currently enrolled courses | Continue on dropping currently enrolled courses | JSON files | Continue JSON files | Group meeting Test cases | Group meeting Handle bugs
| What will you work on today? | Drop currently enrolled courses | Continue on dropping currently enrolled courses | Work on other projects | Continue JSON files | Group meeting Test cases | Group meeting Manual test cases | Slides for presentation Rehearse for presentation
| Do you have any obstacles? | No | No | No | No | No | No | No
Sherman | What did you do yesterday? | Work on other projects | Drop currently enrolled courses | Continue on dropping currently enrolled courses | JSON files | Continue JSON files | Group meeting Test cases | Group meeting JSON files
| What will you work on today? | Drop currently enrolled courses | Continue on dropping currently enrolled courses | Work on other projects | Continue JSON files | Group meeting Test cases | Group meeting JSON files | Slides for presentation Rehearse for presentation
| Do you have any obstacles? | No | No | No | No | No | No | No
YZ | What did you do yesterday? | Work on other projects | Process successful bids for round 2 | Continue successful bids | Work on other projects | Continue successful bids | Group meeting Test cases | Group meeting JSON files
| What will you work on today? | Process successful bids for round 2 | Continue successful bids | Work on other projects | Continue successful bids | Group meeting Test cases | Group meeting JSON files | Slides for presentation Rehearse for presentation
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 9
Person | Question | Week: 14 Oct 2019 to 20 Oct 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | Slides for presentation | Bug fixes and online review | Start abit on round 2 clearing logic, other school commitments | continue working on round 2clearing logic | finishing up round 2 | fell sick, non working day | JSON APIS and round 2
| What will you do today? | Online Review | Start abit on round 2 clearing logic, other school commitments | continue working on round 2clearing logic | finishing up round 2 | continue working on round 2clearing logic | continue working on round 2clearing logic | finishing round 2 clearing logic
| Do you have any obstacles? | No | no | no | no | no | no | no
Joshua | What did you do yesterday? | Slides for presentation | testcases and online review | other project commitments | manual test cases and changing result table | other projects | other projects | testing and integration
| What will you work on today? | Online Review | other project commitments | start on testcases (manual) | other projects | other projects | testing and integration | non-working day
| Do you have any obstacles? | No | no | no | no | no | no | no
Giles | What did you do yesterday? | Slides for presentation | Testcases and online review | update schedule and metrics | Daily updates and minor tweaks to authenticate form | other projects | other projects | Bugs metric + reviewing of codes
| What will you work on today? | Online Review | update schedule and metrics | Daily updates and minor tweaks to authenticate form | other projects | other projects | testing and integration | Shopee competition, non-working day
| Do you have any obstacles? | No | no | no | no | no | no | no
Sherman | What did you do yesterday? | Slides for presentation | AWS deployment and online review | bug fixes and other commitment | other commitments | Json checker files | other commitments | JSON APIS and round 2
| What will you work on today? | Online Review | bug fixes and other commitment | continue on bug fixes and focusing on other commitment | Json checker files | other commitments | testing and integration | finishing round 2 clearing logic
| Do you have any obstacles? | No | no | no | no | no | no | no
YZ | What did you do yesterday? | Slides for presentation | slides and online review | other school projects | read up on json test cases | non-working day | Other projects | Change input for API testcases
| What will you work on today? | Online Review | start on test cases (json) | start on test cases (json) | Other projects | Other projects | work on more testcases | non-working day
| Do you have any obstacles? | No | no | no | No | no | no | no

## Week 10
Person | Question | Week: 21 Oct 2019 to 27 Oct 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | finishround 2 logic | bug fixes and testing | non working day | Idp grp proj | working | bugs metric/testcases | fixing round 2 logic bugs
| What will you do today? | testing & integration | non working day | Idp grp proj | working | bugs metric/testcases | fixing round 2 logic bugs | self manual testing of features
| Do you have any obstacles? | no | no | no | no | no | no | no
Joshua | What did you do yesterday? | update json delete bid | bug fixes and testing | non working day | bpas meeting | bpas report | bugs metric/testcases | other school commitments
| What will you work on today? | test cases and testing | non working day | bpas meeting | bpas report | bugs metric/testcases | other school commitments | self manual testing of features
| Do you have any obstacles? | no | no | no | no | no | no | no
Giles | What did you do yesterday? | non working day | testing and reviewing of schedules | non working day | bpas report | checking JSON APIs | Checking of testcases and functions | revising schedule + minutes
| What will you work on today? | testing & integration | non working day | other school commitments | checking JSON APIs | testcases | revising schedule + minutes | self manual testing of features
| Do you have any obstacles? | no | no | no | no | no | no | no
Sherman | What did you do yesterday? | finishround 2 logic , | testing and integrations | other school proj | other school proj | IDP project | Generated testcases for json checker | fixing round 2 logic bugs
| What will you work on today? | testing & integration | other school proj | other school proj | IDP project | testcases | fixing round 2 logic bugs | self manual testing of features
| Do you have any obstacles? | no | no | no | no | no | no | no
YZ | What did you do yesterday? | update json delete bid | testing and integrations | non working day | non working day | non working day | bugs metric/testcases | other school commitments
| What will you work on today? | testing & integration | non working day | non working day | non working day | testcases | other school commitments | self manual testing of features
| Do you have any obstacles? | no | no | no | no | no | no | no

## Week 11
Person | Question | Week: 28 Oct 2019 to 3 Nov 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | self manual testing of features | functionalities test | fix update bid function | test functionalities | dataset test | fix edollar | compile bugs from UAT
| What will you do today? | testing of functionalities | fix update bid function | testing of functionalities | test dataeset | update bid function | deployment | fix bugs in local version
| Do you have any obstacles? | no | no | no | no | no | no | no
Joshua | What did you do yesterday? | self manual testing of features | fix token error | fix token error | test APIS | update JSON cheker file | change JSON checker files | compile bugs from UAT
| What will you work on today? | testing of json APIS | JSON testcase | testing of JSON APIS | fix issues for UAT | update JSON | deployment | fix bugs in local version
| Do you have any obstacles? | no | no | no | no | no | no | no
Giles | What did you do yesterday? | self manual testing of features | fix vacancy bugs | fix token error | JSON API test | update JSON cheker file | change JSON checker files | compile bugs from UAT
| What will you work on today? | testing of bootstrap validations | fix token issues in JSON checker | testing of JSON APIS | fix issues for UAT | fix issue in dataset | deployment | fix bugs in local version
| Do you have any obstacles? | no | no | no | no | no | no | no
Sherman | What did you do yesterday? | self manual testing of features | CT project | bootstrap validation | fixed bootstrap | fix bootstrap | fix bootstrap | compile bugs from UAT
| What will you work on today? | testing of bootstrap validations | bootstrap validation | fix bugs in start/stop round | test dataeset | bootstrap fix | deployment | fix bugs in local version
| Do you have any obstacles? | no | no | no | no | no | no | no
YZ | What did you do yesterday? | self manual testing of features | OOP proj | test JSON checker | OOP project | update JSON cheker file | change JSON checker files | compile bugs from UAT
| What will you work on today? | testing of bootstrap validations | fix issues in JSON checker | fix issues in JSON checker | update testcases for JSON checker | update JSON cheker file | deployment | DA project
| Do you have any obstacles? | no | no | no | no | no | no | no

## Week 12
Person | Question | Week: 4 Nov 2019 to 10 Nov 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | fix bugs found in UAT | fix bugs found in UAT | update BidDAO | change UI | fix bug for clear logic | fixing bug | manually test
| What will you do today? | fix bugs found in UAT | fix bugs found in UAT | change UI | update BM | update UI | manually test | manually test
| Do you have any obstacles? | no | no | no | no | no | no | no
Joshua | What did you do yesterday? | compile bugs from UAT | BPAS project | view result function | successful bid function | CT project | fixing bug | manually test
| What will you work on today? | BPAS project | Bid status JSON | logout function | CT project | fix bug for drop section | manually test | BPAS project
| Do you have any obstacles? | no | no | no | no | no | no | no
Giles | What did you do yesterday? | compile bugs from UAT | CT project | manually test | CT project | manually test | fixing bug | manually test
| What will you work on today? | CT project | manually test | CT project | manually test | JSON checker | manually test | CT project
| Do you have any obstacles? | no | no | no | no | no | no | no
Sherman | What did you do yesterday? | fix bugs found in UAT | CT project | manually test | fix bugs | manually test | fixing bug | manually test
| What will you work on today? | CT project | fix bugs found in JSON checker | fix clear logic | manually test | fix bugs | manually test | CT project
| Do you have any obstacles? | no | no | no | no | no | no | no
YZ | What did you do yesterday? | compile bugs from UAT | DA project | compute bug metric | OOP project | manually test | OOP project | manually test
| What will you work on today? | DA project | compute bug metric | OOP project | manually test | OOP project | manually test | OOP project
| Do you have any obstacles? | no | no | no | no | no | no | no

## Week 13
Person | Question | Week: 11 Nov 2019 to 17 Nov 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday? | mannually test | bug fixing manually | bug fixing | finding corner cases | finding corner cases | finding corner cases
| What will you do today? | bug fix | continue bug fixing | finding corner cases | finding corner cases | finding corner cases | Preparing for final presentation
| Do you have any obstacles? | no | no | no | no | no | no
Joshua | What did you do yesterday? | BPAS project | Slides for presentation | helping with slides for final preentation | finding corner cases | finding corner cases | finding corner cases
| What will you work on today? | Slides for presentation | Slides for presentation | finding corner cases | finding corner cases | finding corner cases | Preparing for final presentation
| Do you have any obstacles? | no | no | no | no | no | no
Giles | What did you do yesterday? | CT project | testcase | testcases | finding corner cases | finding corner cases | finding corner cases
| What will you work on today? | testcase | testcase | finding corner cases | finding corner cases | finding corner cases | Preparing for final presentation
| Do you have any obstacles? | no | no | no | no | no | no
Sherman | What did you do yesterday? | CT project | bug fix | Final presentation slides | Final presentation slides | Final presentation slides | Final presentation slides
| What will you work on today? | bug fix | Final presentation slides | final presentation slides | Final presentation slides | Final presentation slides | Preparing for final presentation
| Do you have any obstacles? | no | no | no | no | no | no
YZ | What did you do yesterday? | OOP project | Compute bug metric | fix json bugs | finding corner cases | finding corner cases | finding corner cases
| What will you work on today? | Compute bug metric | fix json bugs | find corner cases | finding corner cases | finding corner cases | Preparing for final presentation
| Do you have any obstacles? | no | no | no | no | no | no

## Week 14
Person | Question | Week: <starting date> to <ending date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Sue-anne | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Joshua | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Giles | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Sherman | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
YZ | What did you do yesterday?
What will you work on today?
Do you have any obstacles?